HEADACHE EVALUATION TOOL Phased Build Plan Milestones, Dependencies & Build Order

Version 1.0  |  March 2026

Tech-Stack Agnostic  |  For Internal Planning Only

# Document Purpose

This document breaks the Headache Evaluation Tool into four buildable phases, each independently deployable and testable. Each phase produces a usable increment of the product. The plan is completely tech-stack agnostic — it defines what to build, in what order, and what blocks what.

Audience: Founder, lead developer, and any future team members joining the build.

Source: Derived from the Developer Implementation Pack (headache_tool_developer_pack.docx) authored by the clinical creator.

# The Four Phases at a Glance

Every phase ends with a working, testable product increment. Phase 1+2+3 together form the complete MVP that a clinic could use on day one.

| Phase | Name | What It Delivers | Exit Condition |
| --- | --- | --- | --- |
| 1 | The Safety Spine | Patient questionnaire, red-flag triage, encounter shell, triage banner | A clinician can receive patient data and triage safety risks |
| 2 | Core Assessment Loop | Full clinician assessment flow (9 screens), real-time scoring sidebar, MVP rules engine | A clinician can walk through a full structured assessment and see live diagnosis ranking |
| 3 | Output & Value | Phenotype output, work-up suggestions, auto-generated clinic note with export | A clinician can complete an encounter end-to-end and produce a signed clinic note |
| 4 | Longitudinal & Extended | Diary/trends, follow-up comparisons, extended diagnosis branches (TACs, NDPH, hypnic, triggered) | The system supports ongoing patient management across multiple visits |

PHASE 1 — THE SAFETY SPINE

Build the foundation that protects patients and collects pre-consultation data. Nothing else works without this.

## What You Build

This phase establishes three things: the data model for encounters and patients, the patient-facing mobile questionnaire, and the red-flag triage system that acts as a safety gate for everything that follows.

### Milestones

| Milestone | What It Delivers | Depends On |
| --- | --- | --- |
| 1.1 — Data Model & Auth | Encounter schema, patient records, clinician accounts, role-based auth (clinician vs system), token generation for patient links | Nothing — this is the start |
| 1.2 — Patient Questionnaire | Mobile-first tokenised form: demographics, headache burden, symptom checklists, warning symptoms, medication exposure. Progress bar, save-and-return, emergency banner on red-flag answers | 1.1 (needs encounter shell and token system) |
| 1.3 — Red-Flag Triage Engine | Backend rule: evaluate SNOOP4 red-flag fields, assign triage level (green/amber/red), generate non-dismissible banner, suspend routine diagnosis labels when red | 1.1 (needs field schema) |
| 1.4 — Clinician Login & Dashboard Shell | Login screen, role-aware redirect, dashboard with patient list, recent encounters, new assessment launcher. No assessment screens yet — just the shell | 1.1 (needs auth and encounter model) |
| 1.5 — Intake Summary Screen | Desktop view of submitted patient questionnaire: demographics, burden, highlighted warning answers, editable fields. Clinician reviews and proceeds | 1.2 + 1.4 (needs patient data and clinician shell) |

## Key Decisions in This Phase

The patient questionnaire token system is a critical design choice. Patients never create accounts — they receive a unique link via email or SMS. That link expires after submission or after a configurable time window. This avoids onboarding friction and keeps the product clinician-centric.

The red-flag engine must be a hard override, not a soft warning. If thunderclap onset or new focal neurology is flagged, the system suspends all routine primary headache labels and shows urgent clinical review recommendations. This is non-negotiable for clinical safety and is the reason this phase exists before any diagnosis logic.

The emergency banner on the patient questionnaire is equally critical. If the patient selects certain warning answers (worst headache of my life, sudden weakness, confusion), they see an immediate on-screen banner advising them to seek emergency care. This fires client-side — it does not wait for a server round-trip.

PHASE 2 — CORE ASSESSMENT LOOP

Build the structured clinical assessment that mirrors how a headache specialist actually thinks.

## What You Build

Nine assessment screens that the clinician walks through in sequence, a rules engine running the five MVP diagnoses, and a real-time scoring sidebar that updates as fields change. This is the clinical brain of the product.

### Milestones

| Milestone | What It Delivers | Depends On |
| --- | --- | --- |
| 2.1 — Schema-Driven Form Renderer | A generic component that reads field definitions from JSON schema and renders the correct control (toggle, slider, multi-select, card grid). New diagnoses and fields can be added without rebuilding screens | 1.1 (needs field schema definitions) |
| 2.2 — Assessment Screens (9 total) | Red flags, Pattern/Chronology, Pain characteristics, Associated symptoms, Aura module (conditional), Autonomic/TAC module, Triggers, Medication exposure, Diary placeholder. Left-nav for jumping between sections. Autosave on section transitions | 2.1 + 1.5 (needs renderer and intake screen) |
| 2.3 — MVP Rules Engine | Implement diagnosis rules for: migraine without aura, migraine with aura, chronic migraine, tension-type headache, cluster headache, and medication-overuse headache. Each rule evaluates required criteria, supporting features, hard exclusions, and downgrade conditions | 1.3 + 2.2 (needs red-flag gate and field data) |
| 2.4 — Real-Time Scoring Sidebar | Sticky right rail showing: current triage colour, top 3 ranked diagnoses with confidence bands, count of missing critical fields, and work-up prompts. Updates on key field changes with debounced server calls | 2.3 (needs rules engine output) |
| 2.5 — Rule Explanation Drawer | Each diagnosis card in the sidebar has a Why? button that opens a drawer showing: criteria met, criteria missing, features arguing against, and confidence band rationale. This is essential for clinical trust | 2.3 + 2.4 |

## Key Decisions in This Phase

The schema-driven form renderer (2.1) is the single most important technical decision in the entire project. If you build forms by hand-coding each screen, every future diagnosis or field addition means rebuilding UI. If you build a renderer that reads from JSON definitions, adding a new headache type means adding a JSON config file — no frontend changes needed. Invest the time here.

The aura and autonomic modules should be conditionally visible. The aura module is hidden unless something in earlier screens suggests aura (or the clinician manually opens it). The autonomic module becomes prominent when strict unilateral severe pain is entered. This mirrors real clinical reasoning — you don't ask irrelevant questions.

Debounce the scoring updates. Don't hit the rules engine on every keystroke. Trigger recalculation on field blur, section save, or after a short idle timeout. This prevents a noisy, flickering sidebar.

PHASE 3 — OUTPUT & VALUE DELIVERY

This is where the clinician feels the payoff — diagnosis output, work-up plan, and the auto-generated note that saves them 10 minutes per patient.

## What You Build

Three screens that complete the clinical workflow: the phenotype output screen (ranked diagnoses with full transparency), suggested work-up (actionable checklist from red flags and escalation rules), and the auto-generated clinic note with manual editing and export.

### Milestones

| Milestone | What It Delivers | Depends On |
| --- | --- | --- |
| 3.1 — Phenotype Output Screen | Top 3 ranked diagnoses with confidence bands (high/moderate/possible), criteria met vs missing vs contradicting, escalation prompts. Each card expands to full rule explanation. Copy-rationale-to-note button | 2.3 + 2.4 (needs rules engine and sidebar) |
| 3.2 — Suggested Work-up Screen | Checklist generated from red flags and escalation rules: urgent review, imaging, labs, ophthalmology, vascular concerns, pregnancy escalation. Clinician accepts or rejects each item. Decisions are logged with timestamps | 1.3 + 3.1 (needs red-flag data and phenotype output) |
| 3.3 — Clinic Note Generator | Auto-populated structured note: presenting pattern, phenotype summary, red flags, medication exposure, burden, and plan. Rich text editor for manual edits. Regenerate button. Export as PDF and DOCX. Mark-as-signed workflow with audit timestamp | 3.1 + 3.2 (needs all upstream data) |
| 3.4 — Encounter Completion Flow | Status transitions: draft > in-progress > ready-for-review > signed. Dashboard reflects status. Signed encounters are locked from editing. Ruleset version is logged against every output for medicolegal traceability | 3.3 + 1.4 (needs note and dashboard) |
| 3.5 — Public Landing Page | Marketing/trust page: product positioning (decision-support, not autonomous diagnosis), clinical references (NICE CG150, ICHD-3, AHS), feature overview, CTA to sign in or request access. No patient-facing public content | Independent — can be built any time |

## Key Decisions in This Phase

The clinic note generator is the feature the doctor who wrote this spec probably dreams about. The note should be structured but editable — clinicians will always want to add personal observations or adjust wording for the GP. The regenerate button should re-pull from the current encounter data, not from a cached version.

Ruleset version logging is non-negotiable. Every generated output must record which version of the rules produced it. If the rules change in v2.0 and a previous case is reviewed in a complaint or audit, the system must show exactly what logic was running at the time. Store the version string, the timestamp, and the raw output immutably.

The landing page (3.5) is listed here but has zero dependencies on anything else. You can build it first as a holding page or last as a polished product page. It does not block any clinical functionality.

PHASE 4 — LONGITUDINAL & EXTENDED DIAGNOSES

The long game — tracking patients over time and expanding the diagnostic coverage beyond core headache types.

## What You Build

Diary and trend tracking, follow-up comparison views, and the extended diagnosis branches that cover the rarer but clinically important headache types: paroxysmal hemicrania, hemicrania continua, SUNCT/SUNA, primary stabbing headache, NDPH, triggered headaches, and hypnic headache.

### Milestones

| Milestone | What It Delivers | Depends On |
| --- | --- | --- |
| 4.1 — Diary & Trend Engine | Calendar view with headache days, severity, medication days, menstrual markers, and triggers. Manual entry and patient diary import. Month-over-month comparison charts. This replaces the placeholder from Phase 2 | 2.2 (needs diary placeholder screen) |
| 4.2 — Follow-up Comparison | Side-by-side encounter snapshots: previous diagnosis ranking vs current, burden delta, treatment changes, response metrics. Only activates once a patient has 2+ encounters | 3.4 (needs completed encounters) |
| 4.3 — Extended Diagnosis Rules | Add rules for: paroxysmal hemicrania, hemicrania continua, SUNCT/SUNA, primary stabbing headache, NDPH, primary cough/exertional/sexual headache, and hypnic headache. These use the same rule format — if 2.1 was built properly, no new UI components needed | 2.3 (needs rules engine framework) |
| 4.4 — Analytics Dashboard | Track: missing-data frequency, red-flag prevalence, diagnosis distribution across all encounters, note edit rate (how much clinicians change the auto-generated note), and questionnaire completion rate | 3.4 (needs completed encounter data) |
| 4.5 — Admin Ruleset Editor (Optional) | A UI for authorised clinicians to view and modify diagnosis rules without touching config files. Lower priority — controlled JSON config files work fine initially | 2.3 (needs rules engine) |

## Key Decisions in This Phase

Phase 4 is deliberately separated because none of it is required for the MVP to work in a real clinic. A headache specialist can absolutely use Phases 1-3 for day-to-day consultations covering the most common headache types. Phase 4 makes the product excellent rather than functional.

The extended diagnosis rules (4.3) are the test of whether you got 2.1 right. If the schema-driven renderer works, adding paroxysmal hemicrania means creating a JSON rule file and potentially adding one or two new fields. If you find yourself rebuilding screens, go back and fix the renderer first.

# Critical Dependency Map

This table shows what blocks what. If a component slips, trace rightward to see the cascade.

| Component | Blocked By | Unlocks | Risk If Late |
| --- | --- | --- | --- |
| 1.1 Data Model & Auth | Nothing | Everything | Total project stop |
| 1.2 Patient Questionnaire | 1.1 | 1.5 Intake Summary | Clinicians have no pre-consult data |
| 1.3 Red-Flag Engine | 1.1 | 2.3 Rules Engine, 3.2 Work-up | Safety gap — critical |
| 2.1 Schema Renderer | 1.1 | All 9 assessment screens | Every screen is hand-coded (debt) |
| 2.3 Rules Engine | 1.3, 2.2 | 2.4 Sidebar, 3.1 Output, 3.2 Work-up | No live diagnosis capability |
| 3.3 Note Generator | 3.1, 3.2 | 3.4 Completion Flow | No workflow value delivery |
| 3.5 Landing Page | Nothing | Nothing (independent) | No external visibility |

# Complete Screen-to-Phase Mapping

Every screen in the product, which phase it belongs to, and what must be working before it can be built.

| Screen | Core UX | Status Gate | Phase |
| --- | --- | --- | --- |
| Login / Role Landing | Email, password, role redirect | Auth system works | Phase 1 |
| Clinician Dashboard | Patient list, encounters, tasks | Auth + encounter model | Phase 1 |
| New Assessment Launcher | Patient search, encounter type, questionnaire invite | Encounter model | Phase 1 |
| Patient Questionnaire (Mobile) | Single-question-per-screen wizard, progress bar, emergency banner | Token system + field schema | Phase 1 |
| Intake Summary | Review patient answers, edit, proceed | Questionnaire submitted | Phase 1 |
| Red Flag Screen | High-contrast warning cards, live triage update | Red-flag engine | Phase 2 |
| Pattern & Chronology | Onset, duration, frequency, pain-free intervals | Schema renderer | Phase 2 |
| Pain Characteristics | Location map, laterality, quality, severity, behaviour | Schema renderer | Phase 2 |
| Associated Symptoms | Grouped checklists, pattern helper chips | Schema renderer | Phase 2 |
| Aura Module | Conditional section — visual, sensory, speech, motor | Schema renderer | Phase 2 |
| Autonomic / TAC Module | Autonomic features card grid | Schema renderer | Phase 2 |
| Triggers | Alcohol, menstrual, exertion, positional, cough | Schema renderer | Phase 2 |
| Medication Exposure | Drug table, days/month, MOH banner | Schema renderer | Phase 2 |
| Phenotype Output | Top 3 diagnoses, confidence bands, Why? drawer | Rules engine | Phase 3 |
| Suggested Work-up | Checklist from red flags + escalation | Red-flag + phenotype output | Phase 3 |
| Clinic Note | Auto-generated, editable, export PDF/DOCX, sign | All upstream data | Phase 3 |
| Public Landing Page | Product positioning, trust anchors, CTA | Independent | Phase 3 |
| Diary & Trends | Calendar, severity chart, import, compare | Encounter data | Phase 4 |
| Follow-up Comparison | Side-by-side encounter snapshots | 2+ completed encounters | Phase 4 |

# Guiding Build Principles

These principles should guide every technical and design decision throughout the build. They come directly from the clinical creator’s intent and the product’s medicolegal context.

## Safety First, Always

The red-flag system is not a feature — it is the product’s ethical backbone. If any code path allows a clinician to reach a diagnosis screen without the red-flag gate having been evaluated, that is a critical defect. The non-dismissible emergency banner exists because people die from missed subarachnoid haemorrhages. Build accordingly.

## Schema-Driven, Not Screen-Driven

Render forms from field definitions. Store field metadata (data type, UI control, conditional visibility, which diagnoses use it) in a structured schema. When the clinical team says "we need to add a field for jaw claudication severity," the answer should be "add it to the schema" — not "rebuild the triggers screen."

## Transparency Over Confidence

Never show a diagnosis without showing why. The Why? drawer, the criteria-met/missing/contradicting breakdown, and the confidence bands are not nice-to-haves. They are what makes this a decision-support tool rather than a black box. Clinicians will not trust a system that says "this is migraine" without explaining its reasoning.

## Immutable Audit Trail

Every generated output must log: which ruleset version produced it, when it was generated, and what raw data it was based on. Never silently overwrite a previous output. If the rules change and the encounter is re-evaluated, store both the old and new outputs. This is a medicolegal requirement, not an engineering preference.

## Separate Raw Data From Derived Outputs

Store patient questionnaire responses and clinician assessment data as raw inputs. Store diagnosis rankings, triage levels, and generated notes as derived outputs in a separate layer. Derived outputs should be versioned and regeneratable from raw inputs at any time.

## The Note Is The Product

Everything in the system ultimately serves the clinic note. The questionnaire collects data for the note. The assessment structures data for the note. The rules engine generates the diagnosis section of the note. The work-up generates the plan section of the note. If the note is good, the clinician saves 10 minutes per patient. If the note is bad, nothing else matters.

# If You Start Tomorrow

Your first three tasks, in order:

- Set up the data model: encounter schema, patient schema, clinician schema, field definitions JSON, and the token generation system for patient questionnaire links. This unblocks everything.

- Build the patient questionnaire as a standalone mobile-first flow with the emergency banner. Test it by sending yourself a token link on your phone. This is your first visible, testable output and it validates the entire token-based access pattern.

- Implement the red-flag triage engine as a backend service that takes field values and returns a triage level. Wire it to a simple test UI. Once this works, you have the safety spine and everything else can build on top of it.

End of Build Plan — Version 1.0